## Sheet1
AT2 RAD
LNL
Nicolas Brown, Liam Saxon, Luke Liston |  |  |  |  | July 15, 2020 | [6 empty] | July 22, 2020 | [6 empty] | July 29, 2020
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Task | Assigned To | Progress | Start | Finish | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Handover
Souce Control Snapshot | Liam Saxon | 100% | 2020-06-12 | 2020-06-19
Update Master Document | Liam Saxon | 100% | 2020-06-12 | 2020-06-19
Software Review Report | Liam Saxon | 100% | 2020-06-12 | 2020-06-19
Project Management Plan | Nicolas Brown | 100% | 2020-06-12 | 2020-06-19
Software Testing Plan | Nicolas Brown | 100% | 2020-06-12 | 2020-06-19
Update Code | Luke Liston, Liam Saxon | 100% | 2020-06-12 | 2020-06-19